## Sheet1
Dylan Farrugia-ATR Project | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Check the components | bar: Week 1
Test the mechanics of vehicle | bar: Week 1 to Week 2
Build main motor picaxe board | bar: Week 2 to Week 3
Wire up main motor board to motors | bar: Week 3
Build second motor board | bar: Week 4
Wire up second motor board to arms control | bar: Week 5
Attach extra power supply | bar: Week 5
Program the system | bar: Week 6 to Week 7
Attatch electronics board to system | bar: Week 8
Test the electronics | bar: Week 8 to Week 9
Repair any faults | bar: Week 9 to Week 10
Test the system | bar: Week 10 to Week 11
Evaluation | bar: Week 12
Complete system log book | bar: Week 12
Proposed: | bar: Week 1
Actual: | bar: Week 1